## Sheet1
# | Reported Date | Reported By | Severity [P0-P5] | Status [open, in-progress, resolved, won't fix] | Assigned To | Short Desc. | Expected Results | Actual Results | Steps to reproduce
M1 Bugs
1 | 2024.10.12 | Raizen | P3 | resolved | TBD | Colliding with wall via recoil while pressing the input key in the opposite direction of the collision, nullifies the movement of that input key until it is pressed again. | Movement should work without the player having to repress the input button | Horizontal movement is stuck until player presses the movement key again | 1. Hold the movement key that moves you in the opposite direction of the wall upon collision. 2. Fire repeatedly in opposite direction of wall to collide with it.
2 | 2024.10.12 | Ayden | P4 | resolved | TBD | Can jump immediatly upon world reset | Player should not be able to jump until they collide with floor | Player can jump in mid-air immediatly upon world reset | 1. Reset world with "R" 2. Immediatly press the jump key
M2 Bugs
3 | 2024.11.02 | Anthony | P3 | resolved | Raizen | When walking very slowly over a corner to drop down, the plsy sometimes experiences rubberbanding issues | Player should be able to fall smoothly over a corner | Player jitters up an down on te corner but are not stuck just need to keep moving | 1.Walk to the right wehre you are about to drop down 3. Walk very slowly towards the edge of the pipe as if you're about to drop down. 4. Once you're almost about to fall there will be a jitter
4 | 2024.11.02 | Sally | P3 | resolved (along with bug 3) | Raizen | mesh resolution jitter when hitting brick corner (same issue source as bug 3 - will get fixed together) | player should not jitter when hitting a brick corner | plager jitter / screen glitch when player hits corner of a brick | 1. find area of expose brick corner (many of them at the "space" tutorial area) 2. jump and land directly on the corner of the brick 3. player jitters hitting the corner
5 | 2024.11.02 | Sally | P3 | resolved | Ayden | no gun auto-reload sound | gun reload sound always plays on reload, no shooting sound | if currently shooting, gun reload sounds gets cut off / not played | 1. keep left clicking even after all ammo used 2. no reload sound heard on auto-reload
6 | 2024.11.02 | Anthony | P3 | resolved | Diana | gun animation continues when not firing | no firing animation when no bullets are shot | firing animation plays when no bullets are fired | 1. hold left click 2. firing animation plays while left click is held down, but no bullets fired
7 | 2024.11.03 | Sally | P3 | open | TBD | player bullet spawing is offset from weapon barrel when facing left | bullets spawn from end of weapon barrel | when facing leftwards, bullets spawn slightly below weapon barrel end | 1. move mouse to be on left-side of player 2. left click to shoot, observe bullet spawn location relative to barrel end
8 | 2024.11.03 | Ayden | P5 | resolved | Raizen | player clips through the ceiling | player collides and stays below ceiling tiles | Player clips through ceiling, sometimes clipping to the left or right | 1. Directly recoil upwards towards the ceiling (must be a ceiling without another floor tile above it) 2. With enough momentum, player either jumps to left or right and clips through ceiling
M3 Bugs
9 | 2024.11.19 | Anthony | P3 | open | Anthony | Grenade spawn over top of the gun | Grenade should only be shown after it leave the barrel of the gun | Grenade is spawning in the middle of the player and showing on top of the gun. | 1. fire the grenade launcher 2. look at where the grenade spawns
10 | 2024.11.19 | Sally | P3 | open | Sally | Player hides inside boss | player receives damage when inside boss enemy near bottom corners (need better fitting collision circle for boss) | Player is able to not recieve damage in bottom corner area of boss | 1. while boss is on the ground, walk into the side of the boss 2. observe player getting no damage while inside boss
11 | 2024.11.19 | Sally | P2 | resolved | Sally/Diana | enemy shoots during death animation | enemy cannot shoot during death animation | sometimes, the enemy is shooting when dying | 1. shoot enemy and kill it 2. if enemy's shoot timer runs out during death timer, it will shoot while death animation is running
12 | 2024.11.19 | Ayden | P2 | resolved | Diana | enemy deals damage when death animation is playing | enemy cannot deal damage when death animation is playing | enemy deals damage when death animation is playing | 1. shoot enemy and kill it 2. if contact with the enemy while it's playing death animation, player can get damaged.
13 | 2024.11.19 | Anthony | P2 | Open | TBD | Very rarely a grenade will go through the wall | Grenade should bounce off the wall always | Grenade sometimes goes through the wall | Steps to reproduce not yet found